## MVP Feature List
# | Module | Feature | Priority | Reason
1 | Customer Side | Login / Registration (phone or email + verification code) | P0 | Orders, addresses and payments must be tied to an identity
2 | Customer Side | Third-party login (WeChat, Google, etc.) | P2 | Convenience only; basic login already works
3 | Customer Side | Product List (basic list with image, title, price, pagination) | P0 | Customers need an entry point to discover products
4 | Customer Side | Product Detail Page (images, price, SKU selector, stock status, description) | P0 | Customers must see product information and select a SKU before ordering
5 | Customer Side | Category Filter (one-level or two-level navigation) | P0 | Minimum browsing structure; without it a catalog of any size is unusable
6 | Customer Side | Keyword Search (basic title match) | P1 | Greatly improves findability, but customers can still browse by category in a small catalog
7 | Customer Side | Search sorting and advanced filters (price, sales, rating) | P2 | Optimization for larger catalogs, not needed to validate the flow
8 | Customer Side | Shopping Cart (add, edit quantity, remove, select items) | P0 | Part of the defined core flow and supports multi-item purchases
9 | Customer Side | Buy Now (single item, skip cart) | P1 | Shortens the path for single-item purchases; cart still covers the need
10 | Customer Side | Submit Order (address, item confirmation, price summary, stock check) | P0 | This is where the order is created; no order means no transaction
11 | Customer Side | Address Management (add, edit, set default) | P0 | Shipping requires a valid address; can be a simple form in MVP
12 | Customer Side | Payment (one primary online channel, payment result page, timeout handling) | P0 | Without payment there is no revenue and the flow cannot proceed to shipment
13 | Customer Side | Multiple payment channels | P2 | One reliable channel is enough to validate; add more by market demand
14 | Customer Side | Order List / Order Detail (status, items, amount, logistics info) | P0 | Customers must confirm the order succeeded and track its progress
15 | Customer Side | Cancel Order (unpaid orders, and paid orders before shipment) | P0 | Basic user control and a prerequisite for releasing locked stock
16 | Customer Side | Refund (full refund for cancelled paid orders) | P1 | Needed for trust and compliance, but can be handled manually by the admin at first
17 | Customer Side | Return / after-sales workflow (partial refund, return logistics) | P2 | Complex process; not required to complete the core flow
18 | Customer Side | Confirm Receipt (with auto-confirm after N days) | P1 | Closes the loop to "Complete Order"; auto-confirm can cover the gap
19 | Customer Side | Coupons, points, promotions | P2 | Growth features; not required for the basic transaction flow
20 | Customer Side | Reviews and ratings, wishlist, recommendations | P2 | Retention and conversion boosters for later iterations
21 | Admin Side | Product Management (create, edit, price, on/off shelf, images) | P0 | Products must exist before they can be sold
22 | Admin Side | Category Management | P0 | Needed to support customer-side category navigation
23 | Admin Side | SKU / Inventory Management (SKU creation, stock view, manual adjustment) | P0 | Prevents overselling and is required to confirm availability at order time
24 | Admin Side | Low-stock alert | P1 | Improves operational efficiency; staff can check manually at first
25 | Admin Side | Bulk import/export of products and stock | P2 | Efficiency tool for large catalogs; manual entry works for MVP
26 | Admin Side | Order Management (list, filter by status/time/order no., view detail) | P0 | Operations must see paid orders to fulfill them
27 | Admin Side | Abnormal order handling (manual close, manual refund, status correction) | P1 | Safety net for payment or stock anomalies; low volume early on, but critical for trust
28 | Admin Side | Shipment Management (select carrier, enter tracking number, mark as shipped) | P0 | Without it the flow cannot move from Paid to Shipped
29 | Admin Side | Logistics API integration and auto-tracking | P2 | Manual tracking number entry is enough for MVP
30 | Admin Side | Batch shipping and print shipping labels | P2 | Efficiency optimization for higher order volume
31 | Admin Side | User Management (staff accounts, basic role permissions: operations vs. admin) | P1 | Needed for access control and audit, but a single shared role can work in early testing
32 | Admin Side | Customer account management (view, disable) | P2 | Not needed for transactions; mainly a risk-control feature
33 | Admin Side | Data Dashboard (orders, GMV, payment success rate, conversion funnel) | P1 | Essential to evaluate the MVP, but not required for orders to flow; can start with simple metrics or a database query
34 | Admin Side | Advanced analytics and reports | P2 | Deeper analysis can wait until there is enough data

## Summary
MVP Priority Summary
Counts update automatically from the 'MVP Feature List' sheet.
Priority | Customer Side | Admin Side | Total | % of Total
P0 | 10 | 5 | 15 | 44.12%
P1 | 4 | 4 | 8 | 23.53%
P2 | 6 | 5 | 11 | 32.35%
Total | 20 | 14 | 34 | 100%
Priority definitions
P0 | Must-have. Without it the basic transaction flow cannot work.
P1 | Should-have. Improves user experience or operational efficiency; a manual fallback exists.
P2 | Nice-to-have. Growth or scale features that can be added in later iterations.
Scoping note
'Buy Now' is rated P1 because the cart already completes the same path. If most purchases are expected to be single-item, promote it to P0 at little extra cost.